# Sustainability Action Plan Matrix

| Sustainability Action | Specific Interventions | Expected Outputs | Resources Required | Lead & Collaborators | Timeline (Short, Medium, Long Term) |
| --- | --- | --- | --- | --- | --- |
| Ownership & Governance | Develop a governance framework Establish a data-sharing framework Develop a data governance structure aligned with national policies | Approved data governance framework Operational data-sharing mechanism Strengthened institutional coordination and accountability | Human resources Data management infrastructure Financial resources | Lead: KMSA Collaborators: Private observing entities and relevant stakeholders | Short-term: Map and identify stakeholders; Convene stakeholder engagement forums Medium-term: Develop, validate, and endorse governance and data-sharing frameworks Long-term: Implement and operationalize the approved frameworks |
| Capacity Development | Conduct training and professional development programs Upgrade connectivity and internet infrastructure Strengthen technical and operational capacity | Skilled and competent workforce Improved connectivity and system performance Enhanced data exchange and service delivery capacity | Human resources Budgetary support Training facilities and ICT infrastructure | Lead: KMSA Collaborators: CGS, WMO | Short-term: Conduct skills-gap assessment; Deliver awareness sessions and basic training Medium-term: Establish specialized teams for infrastructure and data management Long-term: Institutionalize continuous professional development and knowledge transfer programs |
| Scalability & Resource Mobilization | Align pilot activities with the EW4All Roadmap Develop a resource mobilization strategy | Sustainable and serviceable observation network Expanded observational coverage Increased partner and donor investment | Budgetary support Resource mobilization strategy Partnerships and donor funding | Lead: KMSA Collaborators: Donors and funding agencies | Short-term: Conduct baseline assessment and develop budget Medium-term: Mobilize resources for implementation Long-term: Scale up and sustain the observational network |
| Peer-to-Peer Support & Community of Practice | Identify and map areas of expertise within teams Promote technical peer support and mentoring Establish communities of practice | Strengthened collaboration and knowledge sharing Enhanced technical support mechanisms Increased innovation and problem solving | Staff time Financial support Collaboration platforms | Lead: KMSA Collaborators: Funding agencies and partner institutions | Short-term: Establish a Technical Working Group and identify priority areas Medium-term: Develop joint proposals for national and regional priorities Long-term: Collaboratively implement regional projects |